## Release 1.11_Stories Execution
Razoo - QA Release 1.11 [13 Jan 2011 - 2 Feb 2011]
Sl. No | Story # | Story Description | Module | Status | Defects Count | Iteration #
1 | 2138 | As a CampaignTeamMember, I should receive a notification when my campaign has ended | Campaign | QA Succeeded | 3
2 | 2143 | As a CampaignAdmin, I should receive a notification after I create a team fundraising page to thank me for creating it | Campaign | QA Succeeded | 1
3 | 2145 | As a site visitor ISBAT search for a campaign | Campaign | QA Failed | 3
4 | 2200 | Cache amount raised, number of fundraisers, and number of donors for campaigns | Hack URL | QA Succeeded | 2
5 | 2202 | As a story page visitor I should not have to see an autoplaying video | Story Page | QA Failed | 1
6 | 2207 | As a StoryPageAdmin ISBAT see better text explaining totals on my donations report | Donation Report | QA Succeeded | 1
7 | 2215 | As a story page visitor I should see a link to get more details on the widget | DonateAnywhere | QA Succeeded | 2
8 | 2240 | Wipe out of Guidestar data (mission, vision) | Story Page | QA Failed | 1
9 | 2246 | As a campaign page visitor ISBAT see which fundraisers have matching grants | Campaign | QA Succeeded | 0
10 | 2247 | As a Campaign Admin ISBAT specify a designation for my campaign | Campaign | QA Succeeded | 0
11 | 2248 | As an OrgAdmin ISBAT see the names of StoryPageAdmins in my donations report | Story | QA Succeeded | 0
12 | 2271 | As a RazAdmin ISBAT to run a qahack to end the Team campaign immediately | Hack URL | QA Succeeded | 1
13 | 2319 | Hack to rebuild the sphinx configurations and reindexes. | Hack URL | QA Needed
14 | 2310 | As a donor ISBAT understand anonymous donations better | Donations | QA Failed | 1
15 | 2305 | As a Team Captain ISBAT have a new campaign automatically associated with a campaign group | Campaign
16 | 2294 | As a Campaign Page Visitor I should see story page admin names more prominently in the leaderboard | Campaign | QA Failed | 2
17 | 2293 | As a Team Captain ISBAT sort my leaderboard alphabetically | Campaign | QA Failed | 1
18 | 2287 | As a Donor ISBAT see the timezone on my receipt, so that I can claim the donation on my taxes | Donations | QA Failed | 1
19 | 2322 | As a RazAdmin ISBAT to associate an existing fundraiser with a campaign | Campaign | QA Failed | 1
20 | 2213 | Revised thank you page with comment in place | Thank You Page
21 | 2306 | As a Widget Viewer ISBAT to see a custom logo for the brand | Widget | QA Succeeded
22 | 2296 | As a Team Captain ISBAT determine whether or not offline donations are accepted | Online/offline donation | QA Failed
23 | 2297 | As a Campaign Page Visitor ISBAT differentiate online and offline donation totals | Online/offline donation | QA Failed
25 | 2311 | As a CMS Page Creator ISBAT embed a "Campaign Group Totals" in a CMS Page | CMS
26 | 2307 | As a CMS Page Creator ISBAT embed a "Campaign Group Leaderboard" in a CMS Page | CMS

## Release 1.11_Line Items
Story # | Line Items | Pass/Fail | Comments
2215 | In the Donate anywhere box, to the right of the "Get the code" link, it should read "or learn more". "learn more" should be a popout to /p/DonateAnywhere | Fail
2207 | 1. On story page donations report, instead of "Grand totals to date" text for totals should read "Totals for [start date of filter] to [end date of filter]" | Fail
| 2. I'm changing this to "through" because I believe that's the proper english way of saying it. | Pass
NOTE: this is only a text change; the functionality of how totals are calculated is fine.
2202 | Visitor should have to click play to play the video on story pages only. | Fail | Not working in IE 7
2143 | 1. Email should be brand specific, including links | Fail | Not received any Email like that
1. Email should be plain text
1. Email should be sent when a team fundraising page gets created
| Sender: support@razoo.com "The Razoo Team" Recipient: CampaignAdmin who created the team fundraiser Subject line should read: Subject: "Your Razoo Team Fundraising Page is Ready!" Body: Dear [Name], Congratulations on creating your team fundraiser! Check it out here: [URL to team fundraising page] We've put together a few suggestions to help you with your team fundraiser: 1. Send your team fundraising page link to your supporters and encourage them to create a fundraiser on Razoo. We recommend reaching out to friends, family, coworkers, and anyone you know who might want to be a part of your team. 2. Follow-up personally with your supporters to ask them to fundraise on your behalf. On average, a single fundraiser raises $500, so the amount your team fundraiser generates is directly related to the number of fundraisers you have. 3. Promote your campaign on Twitter and Facebook. Engage your supporters in ongoing dialogue and consider creating a campaign hashtag so people can easily follow your campaign tweets on Twitter. 4. Update your email signature to raise awareness for your fundraiser by including a catchy tag line that promotes your campaign and cause. Thank you so much for your generous efforts! We're excited to help you mobilize your supporters and run a successful campaign. Please contact us at support@razoo.com or (866) 437-1952 if we can help you in any way. Sincerely, The Razoo Team support@razoo.com (866) 437-1952 | Fail | Dear camp Oxfam, Congratulations on creating your team fundraiser! Check it out here: http://www-qatrunk.razoo.com/team/149 We've put together a few suggestions to help you with your team fundraiser: 1. Send your team fundraising page link to your supporters and encourage them to create a fundraiser on Razoo. We recommend reaching out to friends, family, coworkers, and anyone you know who might want to be a part of your team. 2. Follow-up personally with your supporters to ask them to fundraise on your behalf. On average, a single fundraiser raises $500, so the amount your team fundraiser generates is directly related to the number of fundraisers you have. 3. Promote your campaign on Twitter and Facebook. Engage your supporters in ongoing dialogue and consider creating a campaign hashtag so people can easily follow your campaign tweets on Twitter. 4. Update your email signature to raise awareness for your fundraiser by including a catchy tag line that promotes your campaign and cause. Thank you so much for your generous efforts! We're excited to help you mobilize your supporters and run a successful campaign. Please contact us at support@razoo.com or (866) 437-1952 if we can help you in any way. Sincerely, The Razoo Team support@razoo.com (866) 437-1952
2138 | 1. Email should be brand specific, including links | Pass
| 1. Email should be plain text | Pass
| 1. Email should be sent after a campaign has ended. The status of campaigns of campaigns should be checked hourly | Pass
| Recipient: CampaignAdmin and any fundraiser who is associated to that team #Subject line should read: Thank you for making a difference #Body: Dear [Team member name], Welcome to the finish line! You raised $[Amount raised on individual fundraiser] for [org name]! Overall, your team raised $[Amount raised by team] and can be viewed here: [link to team fundraiser]. Please let us know if there's anything we can do for you. Thank you so much for your generous efforts! Sincerely, The Razoo Team support@razoo.com (866) 437-1952 | Pass
2246 | 1. Rightmost column of leaderboard should have the title "match" | Pass
| 1. Remove the grey "donate" buttons | Pass
| 1. If a FR has an active matching grant, the x2 money icon should appear in this column. If a FR does not have one, it should be blank. | Pass
| 1. If no FRs on the team have an active matching grant, this column should not appear | Pass
| 1. The leaderboard should always occupy 100% of the width (i.e., if the "match" column doesn't appear, the table should resize to fill the space) | Pass
2240 | If the Org has an org admin, then copy the mission+vision into the "story" field unless a "story" is already there | Fail | before adding an ORG Admin to the ORG, immediately after creating and changing the audit status, the mission+vision content is displayed.
| Otherwise, remove mission and vision | Pass
2145 | 1. Campaigns should show in search results | Pass
| 2. There should be a checkbox Next to the "Fundraisers" Checkbox that says "Teams". By default, it should be checked. This is a filter for only showing campaigns | Pass
3. The search result itself should show the following:
| 1. Picture should show the logo image of the campaign, appropriately cropped to 120x120. If there is no campaign logo image, show the default image. | Fail
| 2. A blue raised so far ribbon should show the amount raised for the campaign to date. NOTE: this may require caching | Fail
| 3. Title of the campaign should show as a link at the top of the search result | Pass
| 4. Summary of the campaign should show below this | Pass
| 5. Logo of recipient org. Text should read "A team fundraiser for [name of recipient org, linked]" | Pass
| 6. Blue button should say "VIEW" | Pass
| 7. Below "VIEW" button, there should be [number of fundraisers] fundraisers and [number of donors] donors. NOTE: this may require caching | Fail
| 4. Campaigns should have the same state and categories as the recipient org. So, when using dropdown filters, campaigns should filter in the same way. If "Matching Grants only" is checked, campaigns should not show. | Pass
2248 | 1. For each donation, the name of the story page admin of the source of the donation should appear in a new column with the title "Page Creator" | Pass
| 1. This column should appear to the right of the "Source" column | Pass
| 1. This should appear on both the /donations page and the CSV download | Pass
| 1. Remove the "Donation method" column from the /donations page (to save space), but keep the data in the downloadable CSV | NA
2247 | 1. Add designation option to the create and edit pages for a campaign | Pass
| 1. FRs that are created as part of that team should have the designation prefilled during create. This should be editable by the FR admin. | Pass
2319 | Hack to rebuild the sphinx configurations and reindexes.
2319 | This is so that searching for campaigns isn't a performance killer. See #2145 Implementation note: consider using a cron job to calculate these values every 15 minutes so that you don't have to worry about all the callbacks: org, fundraiser, donation, adjustments, etc. | Fail
2271 | Here is the way to test it: 1. create a campaign. Once the campaign is create you will be redirected to url that looks like http://.../team/5, where 5 is the company id. Use it in the next step 2. hit the following URL: http://www-qaserver/admin/end_campaign/5 - this will set the end date for a campaign with id 5 to the past, i.e. make it ended 3. hit the following URL: http://www-qaserver/admin/trigger_campaign_ended_notification_emails - this will send end campaign mail notifications to all ended campaigns. Please note that notification for single campaign goes to multiple recipients. This should only send the notification once for each ended campaign (i.e. hitting the link second time won't send notification) qaserver refers to the qa environment(qatrunk, qa) that is being used. | Pass
2310 | New Text to read: "I would like to make this donation anonymously. Hide my contact information from:" | Fail | IE 7.0 - Mis alignment
2305 | 1. Should be able to create a link to a new campaign that includes a campaign group identifier |  | Cannot test now
2. That campaign group identifier should be a hidden field - the user shouldn't see it in the form
3. The campaign should be associated to that campaign group upon creation
QA: there is no clean way to test this story. So it can be marked as done when one of two dependent stories #2307 or #2311 are done
2294 | 1. Swap the name and fundraiser titles in the leaderboard | Pass
| 2. Text should read "John Smith<br />Fundraising for [fundraiser name]". | Pass
| 3. Both the fundraiser person's name and the fundraiser name (but not "fundraising for") should link to the fundraiser page. | Fail
2293 | 1. Team Captain should be able to select "Alphabetically" from Leaderboard Order | Pass
| 2. Stories in the leaderboard should then be listed alphabetically by the story page admin's name (last name and then first name) | Fail
| 3. Leaderboard rank should not be shown for these fundraisers on the story page. Instead, it should be the same text that appears before the Campaign starts: "A member of [Campaign Name]". | Pass
2287 | 1. The full date w/ timezone should be added after all dates/times for the donation on the donation receipt email | Fail
| 2. The full date w/ timezone should be added after all dates/times for the donation on the donation receipt web page | Pass
| 3. The Date format should be "November 16, 2010 4:34am Eastern Time (US)". The hour should be 12-hour, no zero padding, and with am/pm. Note that we're not saying EST or EDT (standard/daylight) | Pass
| 4. The Date format should change in the "view receipt" as well, and in that, the Date of the email (under the subject) should be the same format [see attached receipt.jpg]. (note that it currently is wrong and shows today's date) | Pass
2322 | 1. The admin screen will take a campaign (urn or drop-down) and a fundraiser (urn) ... or something on story page for raz admins - whatever's easiest within reason (talk to CS team for what's easiest) | Pass
| 2. This will not impact the campaign fee / % for the existing donations | Pass
| 3. The leaderboard totals (dollars and donors) for the fundraisers will match that of the fundraiser's | Fail
| 4. The campaign totals (# of fundraisers, $ raised, and donors) will be updated to include the fundraiser's | Fail
| 5. The total in thermometer will reflect the new fundraiser's total | Fail
| 6. The recent comments and donations at the bottom will reflect any new donations or comments to the fundraiser | Fail
| 7. Should not be allowed to do this for a FR already attached to a campaign (admin must first detatch, then add). Show an error or something... | Fail
| Added AC from Ian's discussion: | Pass
| 1. When creating the association, Set the end date of the Fundraiser to that of the Campaign (added by BF, 1/21) | Pass
| 2. When creating the association, Set the Fundraiser's designation to that of the Campaign (added by BF, 1/21) | Pass
| 3. When creating the association, DO NOT touch the Donations' designations (added by BF, 1/21) | Pass
| 4. When creating the association, the donations should be stamped with the campaign (regardless of whether or not it was disbursed) (added by BF, 1/21) | Pass
2213 | 1. Remove video from thank you page
2. Replace with comment in place (see attached for help on layout)
3. Title should read "Anything encouraging to say about [name of story]?"
4. There should be a textbox with greyed out text that says "Type your message of support here"
5. Below this, for guest donors, there should be a create account option:
1. Title should read "Account"
2. Text should read "You need a Razoo account post this comment. It's really easy to set one up!"
3. "Choose a password" field should appear at top
4. First name, last name, and email fields should show below and be prefilled with information from donation form
5. Text below should read "By clicking the Post Comment button, you are agreeing to our terms and conditions." where terms and conditions is a popout tohttp://www.razoo.com/p/security_privacy_terms
6. Green button should read "POST COMMENT"
7. See http://razoo-dev.clearleft.com/process/donate/thanks.php for additional help on layout
6. For logged in donors, there should be a green button that says "POST COMMENT"
7. Clicking button should post comment to story page and AJAX in the share interface. See #2214
2306 | 1. Matt has the logo - it's the same size | Pass
| 2. This should only apply to GiveMN - not other brands (but if other brands get images, they should be used) | Pass
| 3. The "Get code" snippets (wherever they appear) should be stamped with the current brand [not done currently] | Pass
2296 | 1. There should be a checkbox on the create and edit campaign pages reading "Allow those fundraising for this campaign to specify offline donations. These donations are not validated and may impact the rankings in the leaderboard."
2. if this checkbox is unchecked then any fundraiser associated to this campaign will not be able to manage offline donations [BF changed - typo, said 'checked']
3. the checkbox is unchecked by default [BF added]
4. all fundraisers not associated with a campaign should allow offline donations
2297 | 1. The total raised thermometer should be a composite including offline donations in blue and online donations in green | Pass
| 2. Underneath the $110 raised of... there should be fine print parentheticals that say "($100 online, $10 offline)" | Failed
2311 | 1. <r:campaign_group:donor_count campaign_group="32" /> outputs the total of the donor count for all the campaigns in the campaign group
2. <r:campaign_group:fundraiser_count campaign_group="32 /> outputs the total number of the fundraisers for all the campaigns in the campaign group
3. <r:campaign_group:donation_total campaign_group="32 /> outputs the donation total added up for all the campaigns in the campaign group
2307 | 1. The leaderboard should include all campaigns in the group
2. The leaderboard should be sorted by total dollars raised (online and offline)
3. The leaderboard should include the name of the team fundraiser and the total, the rank, # of donors, and number of fundraisers in the campaign
4. The leaderboard table should have a css class of "campaign-group-leaderboard" so that it can be styled in the CSS
5. The leaderboard should use semantic html - table, table headers and rows...
6. See [[http://www.razoo.com/p/holiday-meta]]